## 1.Water Supply Scheme
Water Supply Schemes
(Rs. In lakh)
Sl. No | Name of the Project | Name of the scheme(AMRUT/UIDSSMT/KFW etc) | Year | Project executed by TWAD/ULB/ others | Date of work order | Target date of completion as per agreement | % of Physical Progress | Project cost in lakhs | Expenditure incurred | Reasion for Delay and Issues if any
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Comprehensive Water Supply Improvement Scheme | TNUDP III | 28.01.13 | CMWSSB | 23.09.13 | 30.04.15 | 99% | 4310 | 4256 | Out of 13410 Nos of HSCs - water meter was fixed for 12360 HSCs.For balance 1050 HSCs meter fixing work is under progress. Trial run will be done on zonal basis Commissioning will be done after the trial run. Probable date of completeion as assured by CMWSSB is 31.03.2020
UGSS SCHEME
Sl. No | Name of the Project | Name of the scheme(AMRUT/UIDSSMT/KFW etc) | Year | Project executed by TWAD/ULB/others | Date of work order | Target date of completion as per agreement | % of Physical Progress | Project cost | Expenditure incurred | Reasion for Delay and Issues if any
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | UGSS | The Proposal is with Municipal Administration and Water Supply Department for Administrative Sanction
Progress of Solid Waste Management- Biomining | [10 empty] | (Rs. In lakh )
S. No. | Location of Durmp yard | Area to be reclaimed | Quantity of Volume in Cu.M | Estimate Amount | Work order Date | Target date of Completion as per agreement | Name of the contractor | Name of Third party verifiction Agency | Quantity of Legacy Waste cheared so far | Expenditure incurred | Reason for delay | Status
|  | (Acre) | [9 empty] | (Indicate appropriate Quantity removed so far)
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Viswesapuram | 4 | 51500 | 267.2 | 18.08.17 | 17.08.18 | Zigma Global Environ Solutions (P) Limited, Erode – 1 | Anna University | 51500 | 267.2 | Site to be handed over by the agency. RDF removal in progress | 51500
Status of Micro Compost Center
SL. NO | Total Quantity of waste Generated (TPD) | Quantity of Bio- degratable waste (TPD) | Total No.of MCC's sanctioned |  | Completed & Put to use |  | On going
|  |  | No. | Total processing capacity (TPD) | No. | Total processing capacity (TPD) | No. | Total processing capacity (TPD)
1 | 3 | 4 | 5 |  | 6 | 7 | 8
1 | 30.9956 | 12 | 7 | 20 | 6 | 20 | - | -
TAMIL NADU UPBAN ROADS INFRASTRUCTURE PROJECT ( TURIP) 2017-18 [ Year wise separate format to be furnished]
SL. No | Estimate Amount | Physical Progress |  |  |  | Expenditure incurred | Probable date of Completion | Reason for delay/Remarks
|  | No. of works taken up | Completed | Progress | To be started
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 500 | 3 | 3 | - | - | 359.12 | - | Completed CR Will be Submitted
TAMIL NADU UPBAN ROADS INFRASTRUCTURE PROJECT ( TURIP) 2018-19 [ Year wise separate format to be furnished]
SL. No | Estimate Amount | Physical Progress |  |  |  | Expenditure incurred | Probable date of Completion | Reason for delay/Remarks
|  | No. of works taken up | Completed | Progress | To be started
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 500 | 3 | 2 | 1 | - | 130.82 | 15.01.2020 | Out of 3 packages, two packages completed and remaining package 4 roads work is in Progress
TAMIL NADU UPBAN ROADS INFRASTRUCTURE PROJECT ( TURIP) 2019-20 [ Year wise separate format to be furnished]
SL. No | Estimate Amount | Physical Progress |  |  |  | Expenditure incurred | Probable date of Completion | Reason for delay/Remarks
|  | No. of works taken up | Completed | Progress | To be started
1 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
1 | 500 | 4 | - | 1 | 3 | 0 | 31.03.2020 | -